## Sheet1
Version | Section | Task Description | Estimate (min) | Estimate (hrs) | Actual (min) | Actual (hrs) | Developer | Schedule | Completed | Reviewed | Reviewer | Status
Foundation- 0.1 | Server | Development Environment | 60 | 1 |  |  |  | 2014-12-03 | 2014-12-09 |  | Dawson
Foundation- 0.1 | Server | Testing Environment | 60 | 1 |  |  |  | 2014-12-03 | 2014-12-09 |  | Dawson
Foundation- 0.1 | Database | Explore current database | 30 | 0.5 |  |  | All | 2014-12-03 | 2014-12-03 |  | Dawson
Foundation- 0.1 | Database | Create User database table | 30 | 0.5 |  |  | Antonio | 2014-12-04 | 2014-12-04 |  | Dawson
Foundation- 0.1 | Database | Create Content database table | 45 | 0.75 |  |  | Damon | 2014-12-04 | 2014-12-04 |  | Dawson
Foundation- 0.1 | Database | Create Subscribed Path database table | 30 | 0.5 |  |  | Antonio | 2014-12-04 | 2014-12-04 |  | Dawson
Foundation- 0.1 | Database | Create Created Path database table | 30 | 0.5 |  |  | Damon | 2014-12-04 | 2014-12-04 |  | Dawson
Foundation- 0.1 | Database | Create Insert scripts on PHP | 45 | 0.75 |  |  | Adam | 2014-12-05 | 2014-12-09 |  | Dawson
Foundation- 0.1 | Database | Create Update scripts on PHP | 45 | 0.75 |  |  | Ryan | 2014-12-05 | 2014-12-09 |  | Dawson
Foundation- 0.1 | Database | Create Delete scripts on PHP | 45 | 0.75 |  |  | Byung | 2014-12-05 | 2014-12-09 |  | Dawson
Foundation- 0.1 | Database | integrate MySQL content database tables with PHP pages | 60 | 1 |  |  | Damon | 2014-12-06 | 2014-12-09 |  | Dawson
Foundation- 0.1 | Database | ensure that all content data is displayed correctly on PHP page | 15 | 0.25 |  |  | Damon | 2014-12-06 | 2014-12-09 |  | Dawson
Viewable- 0.2 | Web Crawler | display query results to the user in the UI | 1000 | 16.6667 |  |  | All | 2014-12-08 | 2014-12-12 |  | Tim | on test sites
Viewable- 0.2 | Templates | create search results page template | 30 | 0.5 |  |  | Antonio | 2014-12-08 |  |  | Tim
Viewable- 0.2 | Page Template | create homepage template | 30 | 0.5 |  |  | Antonio | 2014-12-08 |  |  | Tim
Viewable- 0.2 | Page Template | create content detail page template | 30 | 0.5 |  |  | Byung | 2014-12-08 |  |  | Tim
Viewable- 0.2 | Homepage | create the Showbiz U top navigation bar with working links (About, Blog, Video, etc.) | 30 | 0.5 |  |  | Damon | 2014-12-09 | 2014-12-10 |  | Tim | on test sites
Viewable- 0.2 | Homepage | create the search bar with fill in function(pressing enter performs search) | 45 | 0.75 |  |  | Ryan | 2014-12-09 | 2014-12-10 |  | Tim | on test sites, no search functionality yet
Viewable- 0.2 | Homepage | create the "Sort by" toggle (sort by most viewed or date) | 45 | 0.75 |  |  | Antonio | 2014-12-09 |  |  | Tim
Viewable- 0.2 | Homepage | create the content items displayed in a row for each type of content (course, video, article, etc.) | 60 | 1 |  |  | Damon | 2014-12-09 |  |  | Tim
Viewable- 0.2 | Homepage | create content to have: type, title, source, date added, type image (optional), "add" button | 40 | 0.66667 |  |  | Byung | 2014-12-09 |  |  | Tim
Viewable- 0.2 | Homepage | have "add" button to tell user to "sign up" and "log in" link | 30 | 0.5 | 270 | 4.5 | Adam | 2014-12-09 | 2014-12-07 |  | Tim | on adamtest
Viewable- 0.2 | Homepage | create the "sign up" and "log in" links (with working links) | 40 | 0.66667 |  |  | Adam | 2014-12-16 |  |  | Tim
Viewable- 0.2 | Homepage | create the content to be in carousel display | 60 | 1 |  |  | Antonio | 2014-12-16 |  |  | Tim
Viewable- 0.2 | Homepage | carousel displays 4-5 content items at a time (find javascript plugin for this) | 30 | 0.5 |  |  | Antonio | 2014-12-16 |  |  | Tim
Viewable- 0.2 | Homepage | create the carousel to rotate through content (for the user to browse by clicking the arrows on the side) | 30 | 0.5 |  |  | Antonio | 2014-12-16 |  |  | Tim
Viewable- 0.2 | Homepage | create the filters on the type to filter the content that is displayed in the carousel (act, dance, music, etc.) | 60 | 1 |  |  | Damon | 2014-12-16 |  |  | Tim
Viewable- 0.2 | Homepage | map correct database content to home view | 30 | 0.5 |  |  | Damon | 2014-12-16 |  |  | Tim
Viewable- 0.2 | Content Page | create content fields: image, title, description | 30 | 0.5 |  |  | Damon | 2014-12-20 |  |  | Tim
Viewable- 0.2 | Content Page | create link to actual content | 35 | 0.58333 |  |  | Damon | 2014-12-20 |  |  | Tim
Viewable- 0.2 | Content Page | integrate with webcrawler/database so fields accurately reflect the content | 60 | 1 |  |  | Damon | 2014-12-20 |  |  | Tim
Viewable- 0.2 | Searching | create the search bar with fill in function(pressing enter performs search) | 30 | 0.5 |  |  | Ryan | 2014-12-23 |  |  | Tim
Viewable- 0.2 | Page Template | create search results page template | [5 empty] | 2014-12-24 |  |  | Tim
Viewable- 0.2 | Searching | create filter navigation bar and display current filter | 60 | 1 |  |  | Adam | 2014-12-26 |  |  | Tim
Viewable- 0.2 | Searching | create each filter and associated page | 120 | 2 |  |  | Damon | 2014-12-26 |  |  | Tim
Viewable- 0.2 | Searching | create result generated in list | 60 | 1 |  |  | Damon | 2014-12-27 |  |  | Tim
Viewable- 0.2 | Searching | create bottom page navigation | 60 | 1 |  |  | Antonio | 2014-12-27 |  |  | Tim
Viewable- 0.2 | Searching | create view more results | 60 | 1 |  |  | Antonio | 2014-12-28 |  |  | Tim
Viewable- 0.2 | Searching | create dynamic links on results to content page | 30 | 0.5 |  |  | Damon | 2014-12-29 |  |  | Tim
Interactive- 0.3 | Web Crawler | query through the crawl results for the best match to the search input | 1000 | 16.6667 |  |  | All | 2014-12-30 |  |  | Tim
Interactive- 0.3 | Facebook Login Popup | create formatted popup | 25 | 0.41667 |  |  | Ryan | 2014-12-30 |  |  | Tim
Interactive- 0.3 | Facebook Login Popup | create recall process of existing facebook/showbizu account | 45 | 0.75 |  |  | Adam | 2014-12-30 |  |  | Tim
Interactive- 0.3 | Facebook Login Popup | close button functionality | 25 | 0.42 |  |  | Ryan | 2014-12-30 |  |  | Tim
Interactive- 0.3 | Facebook Login Popup | confirmation button functionality | 25 | 0.42 |  |  | Ryan | 2014-12-30 |  |  | Tim
Interactive- 0.3 | Facebook Login Popup | send fields to database and search in User database table, return success/failure | 45 | 0.75 |  |  | Damon | 2014-12-30 |  |  | Tim
Interactive- 0.3 | Facebook Signup | create formatted popup | 25 | 0.41667 |  |  | Ryan | 2014-12-31 |  |  | Tim
Interactive- 0.3 | Facebook Signup | create integration process of facebook information to showbizu | 45 | 0.75 |  |  | Damon | 2014-12-31 |  |  | Tim
Interactive- 0.3 | Facebook Signup | close button functionality | 20 | 0.33 |  |  | Ryan | 2014-12-31 |  |  | Tim
Interactive- 0.3 | Facebook Signup | confirmation button functionality | 20 | 0.33 |  |  | Ryan | 2014-12-31 |  |  | Tim
Interactive- 0.3 | Facebook Signup | create new user entry in database, ensure all information is accurate, and marked as Facebook account | 45 | 0.75 |  |  | Damon | 2014-12-31 |  |  | Tim
Interactive- 0.3 | Login Popup | create popup with formatted text, textboxes, and links | 30 | 0.5 |  |  | Ryan | 2014-01-01 |  |  | Tim
Interactive- 0.3 | Login Popup | create authentication process with email and password field | 60 | 1 |  |  | Adam | 2014-01-01 |  |  | Tim
Interactive- 0.3 | Login Popup | create incorrect credentials process with email and password field | 30 | 0.5 |  |  | Damon | 2014-01-01 |  |  | Tim
Interactive- 0.3 | Login Popup | create password retreival process using only email | 60 | 1 |  |  | Damon | 2014-01-01 |  |  | Tim
Interactive- 0.3 | Login Popup | close window function using close button | 20 | 0.33 |  |  | Ryan | 2014-01-01 |  |  | Tim
Interactive- 0.3 | Login Popup | create facebook login button functionality | 20 | 0.33 |  |  | Ryan | 2014-01-01 |  |  | Tim
Interactive- 0.3 | Login Popup | send fields to database and search in User database table, return success/failure | 45 | 0.75 |  |  | Damon | 2014-01-01 |  |  | Tim
Interactive- 0.3 | Signup Popup | create popup with formatted text, textboxes, and links | 30 | 0.5 |  |  | Ryan | 2014-01-02 |  |  | Tim
Interactive- 0.3 | Signup Popup | create process to confirm passwords match | 30 | 0.5 |  |  | Ryan | 2014-01-02 |  |  | Tim
Interactive- 0.3 | Signup Popup | create process to confirm terms agreement | 30 | 0.5 |  |  | Adam | 2014-01-02 |  |  | Tim
Interactive- 0.3 | Signup Popup | create process of inputting new user information into database | 60 | 1 |  |  | Adam | 2014-01-02 |  |  | Tim
Interactive- 0.3 | Signup Popup | create email validation process | 60 | 1 |  |  | Damon | 2014-01-02 |  |  | Tim
Interactive- 0.3 | Signup Popup | create facebook sign up button functionality | 25 | 0.42 |  |  | Ryan | 2014-01-02 |  |  | Tim
Interactive- 0.3 | Signup Popup | cancel button functionality | 25 | 0.42 |  |  | Ryan | 2014-01-02 |  |  | Tim
Interactive- 0.3 | Signup Popup | create new user entry in database, ensure all information is accurate | 30 | 0.5 |  |  | Damon | 2014-01-02 |  |  | Tim
Interactive- 0.3 | Created Path Container Page | create search input and button | 40 | 0.67 |  |  | Adam | 2014-01-03 |  |  | Tim
Interactive- 0.3 | Created Path Container Page | create place to hold all created paths | 120 | 2 |  |  | Antonio | 2014-01-03 |  |  | Tim
Interactive- 0.3 | Created Path Container Page | create created path template | 120 | 2 |  |  | Antonio | 2014-01-03 |  |  | Tim
Interactive- 0.3 | Created Path Container Page | create create new path button | 50 | 0.83 |  |  | Adam | 2014-01-03 |  |  | Tim
Interactive- 0.3 | Created Path Container Page | create search for Created Paths | 120 | 2 |  |  | Adam | 2014-01-03 |  |  | Tim
Interactive- 0.3 | Create New Path Popup | create path name input | 20 | 0.33 |  |  | Adam | 2014-01-04 |  |  | Tim
Interactive- 0.3 | Create New Path Popup | create description textarea | 20 | 0.33 |  |  | Adam | 2014-01-04 |  |  | Tim
Interactive- 0.3 | Create New Path Popup | create submit button | 20 | 0.33 |  |  | Adam | 2014-01-04 |  |  | Tim
Interactive- 0.3 | Create New Path Popup | create cancel button | 20 | 0.33 |  |  | Adam | 2014-01-04 |  |  | Tim
Interactive- 0.3 | Create New Path Popup | create functionality where a new path will be created | 120 | 2 |  |  | Adam | 2014-01-04 |  |  | Tim
Interactive- 0.3 | Page Template | create paths page template | 30 | 0.5 |  |  | Antonio | 2014-01-04 |  |  | Tim
Interactive- 0.3 | Created Path Page | create list that holds content | 90 | 1.5 |  |  | Antonio | 2014-01-05 |  |  | Tim
Interactive- 0.3 | Created Path Page | create redirect when user clicks content | 30 | 0.5 |  |  | Antonio | 2014-01-05 |  |  | Tim
Interactive- 0.3 | Created Path Page | create finished button | 30 | 0.5 |  |  | Adam | 2014-01-05 |  |  | Tim
Interactive- 0.3 | Created Path Page | create incompleted content tab page | 60 | 1 |  |  | Antonio | 2014-01-05 |  |  | Tim
Interactive- 0.3 | Created Path Page | create completed content tab page | 60 | 1 |  |  | Antonio | 2014-01-05 |  |  | Tim
Interactive- 0.3 | Created Path Page | create way to move content to finished tab page | 180 | 3 |  |  | Antonio | 2014-01-05 |  |  | Tim
Interactive- 0.3 | Created Path Page | create visualization for finished/unfinished ratio | 180 | 3 |  |  | Antonio | 2014-01-05 |  |  | Tim
Interactive- 0.3 | Created Path Page | create button to delete from path | 30 | 0.5 |  |  | Adam | 2014-01-05 |  |  | Tim
Interactive- 0.3 | Created Path Page | create functionality that deletes from the path | 120 | 2 |  |  | Adam | 2014-01-05 |  |  | Tim
Interactive- 0.3 | Search Results [logged in] | create add to path button and functionality | 60 | 1 |  |  | Adam | 2014-01-05 |  |  | Tim
Interactive- 0.3 | Subscribed Paths Container Page | create search input and button | 30 | 0.5 |  |  | Adam | 2014-01-05 |  |  | Tim
Interactive- 0.3 | Subscribed Paths Container Page | create place to hold all subscribed paths | 120 | 2 |  |  | Antonio | 2014-01-05 |  |  | Tim
Interactive- 0.3 | Subscribed Paths Container Page | create subscribed path template | 120 | 2 |  |  | Antonio | 2014-01-05 |  |  | Tim
Interactive- 0.3 | Subscribed Paths Container Page | create search for Subscribed Paths | 120 | 2 |  |  | Adam | 2014-01-05 |  |  | Tim
Interactive- 0.3 | Subscribed Paths Page | create list that holds content | 90 | 1.5 |  |  | Antonio | 2014-01-06 |  |  | Tim
Interactive- 0.3 | Subscribed Paths Page | create redirect when user clicks content | 30 | 0.5 |  |  | Antonio | 2014-01-06 |  |  | Tim
Interactive- 0.3 | Subscribed Paths Page | create finished button | 30 | 0.5 |  |  | Antonio | 2014-01-06 |  |  | Tim
Interactive- 0.3 | Subscribed Paths Page | create unfinished tab page | 60 | 1 |  |  | Antonio | 2014-01-06 |  |  | Tim
Interactive- 0.3 | Subscribed Paths Page | create finished tab page | 60 | 1 |  |  | Antonio | 2014-01-06 |  |  | Tim
Interactive- 0.3 | Subscribed Paths Page | create way to move content to finished tab page | 180 | 3 |  |  | Antonio | 2014-01-06 |  |  | Tim
Interactive- 0.3 | Subscribed Paths Page | create visualization for finished/unfinished ratio | 180 | 3 |  |  | Antonio | 2014-01-06 |  |  | Tim
Interactive- 0.3 | Page Template | create user profile page template | 30 | 0.5 |  |  | Byung | 2014-01-06 |  |  | Tim
Interactive- 0.3 | Profile | create image box that reflects the image uploaded in the Settings--if no uploaded image, use default picture | 40 | 0.67 |  |  | Adam | 2014-01-07 |  |  | Tim
Interactive- 0.3 | Profile | display Name text specified in Settings under the image | 30 | 0.5 |  |  | Byung | 2014-01-07 |  |  | Tim
Interactive- 0.3 | Profile | create About Me, My Interests, and Subscribed Paths sections that pull appropriate information and display them | 120 | 2 |  |  | Byung | 2014-01-07 |  |  | Tim
Interactive- 0.3 | Settings | create image box with camera icon on bottom right--icon links to popup | 45 | 0.75 |  |  | Adam | 2014-01-07 |  |  | Tim
Interactive- 0.3 | Settings | implement upload image functionality to support only jpg, gif, png files | 40 | 0.67 |  |  | Adam | 2014-01-07 |  |  | Tim
Interactive- 0.3 | Settings | create pencil icon button, links dynamically to editable fields | 35 | 0.58 |  |  | Byung | 2014-01-07 |  |  | Tim
Interactive- 0.3 | Settings | create ability to edit text fields (name, city, school, company, email) | 35 | 0.58 |  |  | Byung | 2014-01-07 |  |  | Tim
Interactive- 0.3 | Settings | create ability to edit radio buttons on the My Interests section--can only select one per row | 35 | 0.58 |  |  | Byung | 2014-01-07 |  |  | Tim
Interactive- 0.3 | Settings | specify required fields using asterisk | 15 | 0.25 |  |  | Byung | 2014-01-07 |  |  | Tim
Interactive- 0.3 | Settings | create Save Changes button that locks edited fields in the database | 30 | 0.5 |  |  | Byung | 2014-01-07 |  |  | Tim
Interactive- 0.3 | Settings | display "All changes have been saved" text after Save Changes button is pressed | 15 | 0.25 |  |  | Byung | 2014-01-07 |  |  | Tim
Foundation- 0.1 | Web Crawler | Trained web crawler | 180 | 3 |  |  | All | 2014-01-08 |  |  | Tim
Foundation- 0.1 | Web Crawler | populate a database of all crawl results | 1000 | 16.6667 |  |  | All | 2014-01-08 |  |  | Tim
MVP- 0.4 | System | final review changes |  |  |  |  | All | 2014-01-09 |  |  | Tim
MVP- 0.4 | System | testing |  |  |  |  | All | 2014-01-30
Note on A1: This is most recent update of our tracking document as of Friday night (12/12). It is constantly being updated as we complete tasks